## Sheet1
Tajikistan Energy Sector Development Matrix, as of 11 Dec 2018
| Development Partners | Project Name | Status | Start | End | Commitment | Geographic area | Key objectives | DPs involved, supporting/having identical goals/objectives | Key indicators | Key outcomes | Type of Assistance (technical/ financial/ other) | Progress/areas for cooperation and coordination | Key partners | Legal Status | Comments / next steps | Contacts
1.1 | WB | CASA-1000 | Ongoing | 2016 | 2020 | 529.75 M USD | Regional | to create the conditions for sustainable electricity trade between the Central Asian countries ofTajikistan and Kyrgyz Republic and the South Asian countries of Afghanistan and Pakistan | IsDB - 70 M USD EIB - 70 M EURO EBRD - 110 M USD USAID - 15 M USD DFID - 31 M GBP | Trade initiated between the participating countries; Commercial framework between the countries is established and operational; Institutional mechanism for project sustainability is in place; Transmission lines constructed under the Project. | General: Greater economic cooperation, contributing to growth, the elimination of extreme poverty and the boosting of shared prosperity, stable export revenue stream for a number of years from electricity export; Tajikistan: the project responds to the expected result of improving the reliability/efficiency of electricity services and increasing energy export potential; helps reduce poverty and vulnerability by maintaining fiscal stability and access to critical public services | Technical and financial | Cooperation/Coordination with EBRD on transparent revenue management by BT/GoT; | MoE, BT | Effective as of January 28, 2018 | Procurement of major CASA infrastructure components is in advanced stage. During summer-fall, 2018 signing of critical packages has taken place with the last infrastructure contract for HVDC line to be signed in early 2019. Preparation of the CSPs is also in the advanced stage. | Takhmina Mukhamedova, Sr. Energy Specialist, tmukhamedova@worldbank.org
1.2 | WB | CASA -1000 Community Support Project | Pipeline | 2019 | 2022 | 26 M - tbd | National | to increase quality of, and access to, energy, social and economic infrastructure services, and contribute to the strengthening of local governance capacity in communities in the project area | IDA Reg-USD $16 M IDA Nat-USD $8 M USD $2 M CASA MDTF (fianced by USAID and DFID) | 1. Percentage of target communities in the CASA-1000 corridor of impact (CoI) with improved access to energy. 2. Percentage of target communities in the project areas with improved access to social infrastructure (including electricity and energy efficiency) as a result of project support (access to social infrastructure improvements /whole of community). 3. Percentage of beneficiaries in target communities who report that: (a) their engagement in decision making over project investments was effective; and (b) investments met their needs (engagement – gender disaggregated/whole of community). 4. Percentage of young (women and men) beneficiaries who report that their role/voice in local decision-making has been enhanced as a result of project support (empowerment/inclusion - gender disaggregated/youth) | Increased quality of, and access to, energy, social and economic infrastructure services, and strengthened local governance capacity in communities in the project area. | Investment Project Financing | under preparation | BT, Energy Sector PMU, NSIFT | under preparation | To approved by the Board of Directors of the WB on March 19, 2019 with expected effectiveness in September 2019 | Takhmina Mukhamedova Sr. Energy Specialist, tmukhamedova@worldbank.org
1.3 | WB | Nurek HPP Rehabilitation Project, Phase I | Ongoing | 2017 | 2022 | 225.7M | National | to rehabilitate and restore the generating capacity of three power generating units of Nurekhydropower plant, improve their efficiency, and strengthen the safety of the Nurek dam | AIIB - 60 M USD EDB - 40 M USD | 1. Generation capacity of energy constructed or rehabilitated under the project; 2. Estimated annual electricity generation of three units included in the scope of the project (GWh); 3. Estimated increase of winter electricity generation of rehabilitated units due to efficiency improvements (GWh); 4. Improved dam safety against hydrological and geological risks; 5. People provided with improved electricity service (Number). | 1. Generation capacity of energy constructed or rehabilitated under the project; 2. Estimated annual electricity generation of three units included in the scope of the project (GWh); 3. Estimated increase of winter electricity generation of rehabilitated units due to efficiency improvements (GWh); 4. Improved dam safety against hydrological and geological risks; 5. People provided with improved electricity service (Number). | Investment lending | Cooperation/Coordination with EBRD/ADB on BT financial recovery; | MoE, BT | Implementation |  | Takhmina Mukhamedova Sr. Energy Specialist, tmukhamedova@worldbank.org
1.4 | WB | Nurek HPP Rehabilitation Project, Phase II | Pipeline | 2020 | TBD | TBD | National | [9 empty] | Takhmina Mukhamedova Sr. Energy Specialist, tmukhamedova@worldbank.org
1.5 | WB | Technical Assitance on Improvement of Power Tariff Setting and Mitigation of Social Impacts on the Poor | Ongoing | 2018 | 2020 | 350 K | National | The main objectives of the proposed activity are to support the Government to: (a) raise the electricity tariffs to cost-recovery levels; (b) mitigate the impacts of increasing electricity tariffs on socially vulnerable consumers; and (c) implement efficient public communication on energy sector related issues | ESMAP - US$350K | (a) Recommendations on new electricity tariff methodology, its implementation, and social protection mechanisms are provided to the Government (b) Capacity of BT and the authorized state body on computation of tariffs as per new methodology is strengthened (c) The Government expenditure on mitigation of the electricity tariff increases is informed | The key results from the proposed activity include: (a) advice to the Government on new cost-recovery tariff methodology and its implementation; (b) strengthening of the capacity of BT and state authorized agency to be responsible for tariff setting to implement the new tariff methodology; (c) providing inputs to the Government on scale and magnitude of poverty impacts from electricity tariff increases and the potential mitigation measures to be used | Bank-executed Analitical work | Cooperation/Coordination with EBRD/ADB on BT financial aspects (tariff increases, tariff methodology, ect); | MoE, BT | ongoing |  | Takhmina Mukhamedova Sr. Energy Specialist, tmukhamedova@worldbank.org
1.6 | WB | Power Sector Financial Recovery Project | Pipeline | 2019 | 2023 | $70 mln | National | The program development objective is to improve the financial viability of the power sector | IDA - US$70 M | (a) setting the power utility Barqi Tojik (BT) on financially sound feet by assessing the interplay of revenues, debts, and assets; (b) outlining a program to bring it to financial viability; (c) developing mechanisms and strategies to mitigate the impact of tariff increases on vulnerable consumers, thereby linking energy-sector and social policies so as to reach the twin objectives of cost-recovery in the energy sector and the protection of the poorest and most vulnerable households (through targeted social assistance); and (d) strengthening coordination, communication, and capacity on energy subsidy reform.. The project’s support to a financial recovery program should improve BT’s liquidity, enable it to recover from its currently very difficult financial standing, and ensure reliable and adequate electricity supply to all consumers over the long term | To bring BT to financial viability | Program-for-Results Financing |  | MoE, BT | under preparation |  | Takhmina Mukhamedova Sr. Energy Specialist, tmukhamedova@worldbank.org
1.7 | WB | Tajikistan Rural Electrification Project | Pipeline | 2019 | 2024 | $70 mln |  | To provide electricity access to target settlements in Khatlon and Gorno -Badakhshan Autonomous regions of Tajikistan | IDA-US$20 M EU-US$23 M EIB-US$19 M SECO-US$4 M | 1. Construction of Sebzor HPP and its connection to the domestic power transmission and Afghan networks 2. Provision of electricity service to target settlements in Khatlon and GBAO regions 3. Technical Assistance for Project Implementation | 1. People provided with new or improved electricity service by household connections. This indicator would aggregate the following data. • People provided with access to electricity services under the project by household connections (grid or off-grid). • Additional generation capacity under the project. 2. Average annual daily duration of electricity supply in GBAO region. This indicator will measure improvements in reliability of supply to consumers by tracking end-user supply outages due to failures of power sector assets, including generation plants. 3. Incremental export revenues of PEC. This indicator will measure additional revenues of PEC from exports of electricity generated by Sebzor HPP | Investment Project Financing |  | MoE, BT, Pamir Energy | under preparation |  | Takhmina Mukhamedova Sr. Energy Specialist, tmukhamedova@worldbank.org
2.1 | USAID | USAID Energy Links project/CASA-1000 Secretariat support |  | 2014-09-01 | 2019-09-01 | $22.8 mln - regional budget | Regional | USAID funds CASA-1000 Secretariat that assists the four countries’ governments, donors and development banks coordinate design, negotiations, and tendering procedures.The objective of Energy Links is to increase national energy security for countries in Central Asia. Project goals include increasing transparent intra- and inter-regional energy trade; improving the legal and regulatory framework and investment climate for the countries’ energy sectors; improving corporate governance, operations and commercialization of the energy companies; and improving energy efficiency and demand-side management so that the countries of Central Asia will increase the sustainability of their energy sectors and increase their ability to provide year-round, reliable power to their citizens. Energy Links will conduct regional activities in Kazakhstan, Kyrgyz Republic, Tajikistan, Turkmenistan, Uzbekistan, Afghanistan, and Pakistan. | ADB/Corporate Solutions project | Number of power sector beneficiaries with improved governance and technical capabilities as a result of USG assistance | Increased transparent intra- and inter-regional energy trade; Improved legal and regulatory framework and investment climate for Tajikistan’s energy sector; Improved corporate governance, operations, and commercialization of energy companies; Improved energy efficiency and demand side management. | Technical assistance (grant) |  | MOEWR and Barki Tojik | MOU between USAID, MOEWR and Barki Tojik |  | Daler Asrorov, Project Management Specialist, dasrorov@usaid.gov
2.2 | USAID | Central Asia Regional Electricity Market (CAREM) program |  | 2018-08-01 | 2021-08-01 | $ 10 mln | Regional | Central Asia has the potential to re-establish a commercially-viable, market-based power system. A Central Asia Regional Electricity Market, or CAREM, will assure the region’s long-term energy security and economic growth and also serve as a platform for an expanded Central Asia-South Asia regional power market. | ADB, WB, JICA, EU | To draft agreements among National Transmission System Operators To support electricity sector Regulation, Governance and Transparency To enhance efficiency, transparency and accountability of market stakeholders To draft Market-based Pricing and Cost Recovery Tariffs. To improve conditions for increased regional trade | Agreements among National Transmission System Operators drafted. Electricity sector Regulation, governance and transparency developed. Efficiency, transparency and accountability of market stakeholders designed. Market-based Pricing and Cost Recovery Tariffs drafted. Regional trade increased . | Technical Assistance | None | MoEW, BT | Initiation | Initial stages for comunication with national counterparts | Daler Asrorov, Project Management Specialist, dasrorov@usaid.gov
2.3 | USAID | USAID Power the Future project |  | 2017-08-01 | 2019-08-01 | $9 mln - regional budget | Regional | Power the Future works on the transition to, adoption, and scale-up of least-cost and low emission energy solutions to create effective enabling environments for private sector investments in low-cost renewable energy and energy efficiency projects. The project is providing technical assistance to increase Central Asian countries use of low-cost renewable energy resources as part of their national energy mix and to modernize grid management practices and introduce market-based approaches that drive down the cost of renewable energy generation. In addition, USAID will work with each country to rebuild regional power markets and lowering costs while diversifying their energy resource mix. | ADB/Corporate Solutions project | Number of power sector beneficiaries with improved governance and technical capabilities as a result of USG assistance | Increased transparent intra- and inter-regional energy trade; Improved legal and regulatory framework and investment climate for Tajikistan’s energy sector; Improved corporate governance, operations, and commercialization of energy companies; Improved energy efficiency and demand side management. | Technical assistance (grant) |  | MOEWR and Barki Tojik |  |  | Daler Asrorov, Project Management Specialist, dasrorov@usaid.gov
3.1 | DFID | CASA 1000 |  | 2015-06-01 | 2017-03-01 | £31m (£25m CDEL, £6m RDEL) | Regional | Facilitate the transmission and trade of surplus summer hydropower from Tajikistan and Kyrgyzstan to energy deficient Afghanistan and Pakistan. | WBG, IsDB, U.S. Government, EBRD, EIB, partner governments. | 1) Improved and reliable energy trade and supply (increase in cross-border transmission capacity); 2) improved private sector investment; 3) improved pro-poor growth across the whole region over time. | 1) Increased industrial productivity; 2) Increased private investment; 3) Increased regional trade; and 4) Improved energy services. | Capital grant funding: £25m / Resource and TA: £6m. | Programme approved and centrally managed | World Bank, MoEWR, MoEDT, EBRD, other partner governments. | Implementation | Agreement on the results framework with the World Bank. First disbursement and implementation through trust fund arrangement with the World Bank. | Shuhrat Mirzoev, Economic Adviser (S-Mirzoev@dfid.gov.uk / 918-611052)
3.2 | DFID | Central Asia Investment Climate Programme (CAICP) |  | 2015-10-01 | 2017-12-01 | £2m | Multi-country | To attract greater investment to the private sector by reducing compliance costs for businesses and facilitating investment for private sector companies. | IFC (WBG), Swiss Government (SECO) | 1) Reforms adopted and implemented to simplify SHPP investment procedures; 2) Pilot projects in PPP terms implemented; 3) Filtering process for SHPP investments completed to identify pipeline of potential future investments. | 1) Compliance cost savings for businesses; 2) Volume of private investment facilitated. | Technical assistance (grant) | Programme extended until the end of 2017 | IFC (WBG), Swiss Government (SECO), SCISPM, Tax Committee, MoEWR | Implementation | MoU has been signed at the International Entrepreneurship Forum (14th October 2015) / Only one of the programme's components focuses on the energy sector. | Shuhrat Mirzoev, Economic Adviser (S-Mirzoev@dfid.gov.uk / 918-611052)
4.1 | ADB | Regional Power Transmission Project | Ongoing | 2011-11-01 | 2020-06-01 | 141M (including 19M Government financing) | Regional | The project's outputs to (i) construct three new 220 kV TL totalling 216 km (Lot 1), (ii) rehabilitate in whole or part of six substations (Lot 2); (iii) install the SCADA system (Lot 3); and (iv) improve Barki Tojik (BT) operational performance under sector operational performance improvement (SOPI) program | N/A | Annual electricity export from Tajikistan to Central Asian countries and Afghanistan will reach at least 700GWh | Expanded and rehabilitated transmission network for regional trade | Grant |  | MEWR, BT and SE PMUES | Became effective on 19 Oct 2010 | All three initial outputs of the projects are successfully completed. In Oct 2017, the grant closing date was extended from 2017 to 2020 to: (i) prepare a new power sector development project; and (ii) complete all activities under the Sector Operational Performance Improvement Program (output 4). | Shukhrat Khojaev, Project Officer, skhojaev@adb.org
4.2 | ADB | Wholesale Metering and Transmission Reinforcement Project | Ongoing | 2015-08-01 | 2020-03-01 | 67M (including 13M Government financing) | National | The project has 2 outputs: (i) wholesale metering and settlement system; and (ii) construction of 92 km of 220kV Rudaki-Ayni TL and rehabilitation of Ayni and Rudaki substations. | N/A | (i) 196 high and medium voltage substations metered and interconnected to central advanced metering infrastructure and settlement system in 2019; (ii) Transmission capacity in Panjakent region increased from 67 MVA in 2013 to 320 MVA in 2019 | Expanded and metered transmission network | Grant |  | BT and SE PMUES | Became effective on 15 April 2015 | Newly constructed Rudaki-Ayni TL and rehabilitated Ayni and Rudaki substations are already energized. As an additional scope ($3M), the rehabilitation works at 110 kV Rudaki switchyard was completed and energized on 30 Sept 2018. | Shukhrat Khojaev, Project Officer, skhojaev@adb.org
4.3 | ADB | Golovnaya 240 MW HPP Rehabilitation Project | Ongoing | 2015-03-01 | 2022-10-01 | 170M (including 34M Government financing) | National | The project has two outputs (i)full replacement of five units (1, 2, 3, 5 and 6); and (ii) rehabilitation of 110 kV and 220 kV switchyards with generation capacity increased from 240 MW to 270 MW. | N/A | The weighted average generation efficiency increased from 83% in 2012 to 94% in 2020 | Increased weighted average generation efficiency of the power plant from maximum 83.8% to 94.4%. | Grant |  | BT and SE PMUES | Became effective on 31 March 2014 | Unit 5 was energized on 8 Nov 2018. Energizing of Unit 6 is scheduled in Aug 2019. | Shukhrat Khojaev, Project Officer, skhojaev@adb.org
4.4 | ADB | Power Sector Development Project | Pipeline | 2019 | 2025 (tentative) | 65M (TBD) | National | To implement unbundling and reform of BT for financial sustainability of the sector, as well as distribution metering in Dushanbe and other 6 cities. | ADB, WB, EBRD | TBD | Functional and unbundled BT with cash flow management mechanism among unbundled companies. Distribution meters installed and functioning in a sustainable manner. | Grant | Coordination among all development partners is needed to support the government's initiatives. | MEWR, BT and SE PMUES | Approval is expected in 2019 | Distribution metering will require management contracts to be in place to secure short to mid-term sustainable management structure of BT. | Yuki Inoue, Finance Specialist (Energy), yinoue@adb.org
4.5 | ADB | Reconnection to the Central Asian power System | Ongoing | 2018 | 2022 | 35M | Regional | To ensure relay protection system is working to enable connection and parallel operation with the Uzbekistan grid. | N/A | TBD | Parallel operation of Uzbekistan and Tajikistan grids. | Grant | USAID supported BT in preparing the TOR for the feasibility study. | MEWR, BT and SE PMUES | Approved on 12 Nov 2018 and signed on 23 Nov 2018. Effectiveness is expected in Q1 2019. | BT and Uzbekistan design institute are working to finalize the parameters and specification needed for the project. Once completed, bidding process will start. | Yuki Inoue, Finance Specialist (Energy), yinoue@adb.org
5 | JICA | Improvement of Substations in Dushanbe | Ongoing | 2017 | 2020 | 2,190 million Japanese Yen (about 20 million US dollars). | Dushanbe city | To improve sustainability of stable and efficient power supply in Dushanbe city through rehabilitation of Promishlennaya substation (near Farovon bazaar) and construction of new Radiostansiya substation (near Amfiteatr). |  |  | - 110kV “Radiostansiya” substation is constructed - 110kV “Promyshlennaya” substation is rehabilitated - Capacity of relevant technical staff of MEWR and BT in rehabilitating outdated power facilities is strenghthened | Grant |  | MEWR, Barqi Tojik | Effective since 2017 | In June 2017 a grant agreement was signed between GoT and JICA on the Project and then in January 2018 OJSHC “Barqi Tojik” signed a contract with Japanese company “Nishizawa” for construction/rehabilitation of the target two substations. | Navruz Khotamov (Program Officer); 55555 4321 (mob); Khotamov-Navruz@jica.go.jp
6.1 | IsDB | CASA-1000 | Ongoing | 2015 | 2020 | USD 70.00 mn | Regional | To develop cross-border transmission interconnection amongst four IDB member countries to facilitate transfer of surplus hydropower in the Kyrgyz Republic and Tajikistan in summer to energy deficit Pakistan and Afghanistan. | EBRD. EIB, DFID, USAID, WB | i) Sustainable, reliable and affordable supply of electricity to Pakistan and Afganistan, and ii) boosting foreign currency earnings to Tajikistan and Kyrgyz republic through monetization of their seasonal surplus hydropower resources. | Transmission of 4,000 GWh annually to Pakistan and Afganistan during the period (April-September) starting June 2021 | Loan |  | MEWR, BT | Not effective yet | Signing of the EPC contract | Daniyar Abylkhan, Project Officer, dabylkhanov@isdb.org
8.2 | IsDB | Reconstruction of Ravshan substation | Ongoing | 2015 | 2018 | USD 13.7 mn | Tursunzade | The project aims at promoting economic growth and improving the living standards in the Tursunzade city and Shahrinav region through supplying reliable electricity to these regions. |  | The project would provide a significant support to agricultural growth and setting up of small industries in these two regions and thus contribute to poverty reduction. | The project will help to reduce the blackout and electricity interruptions in the two areas from 1072 hours/year in 2012 to 48 hours/year in 2018 and will allow supply of electricity to additional 135,000 inhabitants. | Loan |  | MEWR, BT | To be completed by Oct/2018 | to finalize the project | Daniyar Abylkhan, Project Officer, dabylkhanov@isdb.org
7 | KOICA | Project for Power Grid Construction and Improvement of Health Environment in Romit district in Tajikistan | Ongoing | 2018 | 2020 | 6 M USD | Romit | A. To reduce power inequity and to improve the quality of life of local residents through the construction of a power grid. B. To improve the quality of life by better health service among remote area. | KOICA | Providing reliable electricity supply, expanding access to electricity for population in remote rural areas, improving the condition of local health environment | Acess to electricity is secured; techincal lossess reduced; health environment is improved with modern equipment on place; capacity of staff at established health clinics increased | Grant | Protocol of discussions was signed between KOICA, MEWR & Vahdat Athoruty | MEWR and Vahdat Athouruty | Power supply component by the end of 2019, Health facility component by the end of 2020 | Engagement of Consulting Firm for project supervision is on progress | Ms. Sunmina Jun (Program Officer, Korea Embassy in Tajikistan), tajik@mofa.go.kr
8.1 | EBRD | CASA-1000 (Cross Regional Power Trade) | Ongoing | 2015 | 2020 | 110M USD | Regional | The Project has an objective of leveraging the hydropower resources of Tajikistan and Kyrgyzstan for supply to the electricity deficient markets in Pakistan and Afghanistan. Key objective of the project is facilitation of the electricity cross-border trade of existing summertime hydropower surplus in Tajikistan and Kyrgyzstan | IsDB - 70 M USD EIB - 70 M EURO EBRD - 110 M USD USAID - 15 M USD DFID - 31 M GBP | - Electricity trade between countries initiated - Improved cash collection ratio of BT - Establishment of a tariff setting unit, independent regulator; new tariff methodology - BT corporate and debt restructuring | Construction of the AC/DC converter station and related infrastructure in Tajikistan as part of the high-voltage transmission line for the Central Asia South Asia Electricity Transmission and Trade Project. | Technical and financial | Cooperation/ coordination with ADB and WB on the company's restructuring, tariff reform and financial recovery of BT. Cooperation with WB on transparent revenue management/ | MoE, BT | Signed | The procurement of EBRD/WB/DFID financed component is underway and the timeline for contract signing is early August 2018. | Veronika Krakovich - KrakoviV@ebrd.com
8.2 | EBRD | Qairokkum HPP - Phase I | Ongoing | 2014 | 2021 | 50M USD | National | The rehabilitation will increase the currently installed capacity of the plant from 126MW to 142MW by installing two new turbines with greater rated capacity. Turbines with greater capacity will prevent unnecessary discharge of water through spillways and generate more electricity with the same flow of water. The project will also raise the safety level of the power plant and strengthen its resilience against the projected impacts of climate change. | PPCR - 21M USD | - Development of a new tariff methodology and tariff increases for recovery of service costs of BT - Corporate restructuring of BT - Adoption of Emergency Response Plan to cover flood response, fire, spills and other emergency events - Development of a protocol setting out the provisions for sharing and using climatological and hydro-meteorological information with Tajik Hydromet | Rehabilitation of two out of six existing generation units at Qairokkum plant. | Technical and financial | Cooperation/ coordination with ADB and WB on the company's restructuring, tariff reform and financial recovery of BT | MoE, BT | Effective | The procurement is underway, contract is expected to be awarded shortly. | Veronika Krakovich - KrakoviV@ebrd.com
8.2 | EBRD | Qairokkum HPP - Phase II | Ongoing | 2018 | 2023 | 38M USD | National | The Project is expected to: - increase the installed capacity by 32 MW which, together with the 16 MW increase under the first phase, will result in an increase of the existing installed capacity from 126MW to 174MW by installing new turbines; - prevent unnecessary discharge of water through spillways and allow generation of more electricity with the same flow of water; - raise the safety level of the power plant and the dam; - strengthen the power plant's resilience to the expected impacts of climate change through continued physical upgrades designed to take into account projected increases in climatic and hydrological variability. | GCF - 50M USD EIB - 38M EUR | - Adoption by the hydropower operator of recommended procedures for using hydro-meteorological information and forecasts - Set-up of the system for climate information exchange | Rehabilitation and modernisation of the hydro-mechanical and electro-mechanical equipment of four out of six units at Qairokkum plant. | Technical and financial | Cooperation/ coordination with ADB and WB on the company's restructuring, tariff reform and financial recovery of BT | MoE, BT | Signed | The procurement is underway, contract is expected to be awarded shortly. | Veronika Krakovich - KrakoviV@ebrd.com
8.3 | EBRD | Sugd - Energy Loss Reduction | Ongoing | 2011 |  | 14.15M USD | National | The Project objectives are to reduce distribution network losses, improve quality of supply and increase energy efficiency in the Sugd region of Tajikistan. | EIB - 7M EUR IFCA - 7M EUR | Metering and billing system; up to 90000 residential and corporate meters; partial rehab of LW power lines | Lot 1: Advanced Metering Infra; Lot 2: 110/10 kv Substation; Lot 3: 110/10 kV substation | Technical and financial | Cooperation/ coordination with ADB and WB on the company's restructuring, tariff reform and financial recovery of BT | [MoE, BT] | Repaying | Lot 1: Advanced Metering Infra - complete; Lot 2: 110/10 kv Substation - complete; Lot 3: 110/10 kV substation - procurement on going, expected completion Q1-2019 | Jamshed Rahmonberdiev - RahmonbJ@ebrd.com
9.1 | OSCE | Support the State Service for Supervision over Hydro Technical Facilities for the effective operation and surveillance of hydro-technical facilities | Completed | 2018-06-01 | 2018-11-01 | 20.000 EUR | National | Development of regulations on the dam safety of hydroelectric reservoirs and capacity building events |  |  |  |  | Cooperation/coordination with MEWR and State Service and UNECE Geneva | MEWR, State Service, UNECE | Completed | N/A | Kai.Wegerich@osce.org; Bakhriniso.Narzullaeva@osce.org
9.2 | OSCE | Seminar on normative legal acts on energy efficiency and energy saving | Completed | 2018-06-01 | 2018-08-01 | 10.000 EUR | National | To conduct a two days training on normative legal acts on energy efficiency and energy saving with practical solutions |  |  |  |  | Cooperation/coordination with Association of Energy Engineers | Association of Energy Engineers, Khukumat of Sughd Region | Completed | N/A | Kai.Wegerich@osce.org; Bakhriniso.Narzullaeva@osce.org
Note on O2: Nargis Esufbekova: GoT side
Note on R2: Nargis Esufbekova: Name, email, tel