United Nations 	Nations Unies

United Nations Gender Theme Group

ANNUAL WORK PLAN 2019

Thematic area leads:

WEE- USAID/UNDP

Women in agriculture and Land reform - FAO

Health, RH, stereotypes - UNFPA

Participation, GEWE, convening and overall coordination – UN Women

| OUTCOME 1: UN, Development Partners, local gender machinery, and CSOs enhanced their capacity and accountability on gender equality and women’s rights |  |  |  |  |
| --- | --- | --- | --- | --- |
| OUTPUT 1: Expanded GTG to jointly design, plan, and implement activities aimed at systematic gender mainstreaming by the State |  |  |  |  |
| Planned Activities | Indicators | Timeline | Responsibility | Budget |
| Activity 1.1: Organise UN GTG meetings on a bi-monthly basis to serve as a venue for coordination, information sharing and development for joint initiatives | Indicator 1.1: Expanded GTG meetings organised at least every other month Baseline: no Target: yes Means of Verification: Minutes of the UN GTG meetings | Bi-monthly | UN GTG | Staff time |
| Activity 1.2: Prepare a joint calendar of events and matrix of initiatives to ensure increased information sharing among UNCT | Indicator 1.2: Calendar of Events developed Baseline: no Target: yes Means of Verification: Calendar of Events | March 2019 | Communication Group, UN GTG | Staff time |
| Activity 1.3: Develop and implement joint events for gender equality and women’s rights incl. in the frame of the International Women’s Day, International Day of the Girl Child, the International Day for the Elimination of Violence against Women / 16 Days of Activism, global policy | Indicator 1.3: Number of events for gender equality and women’s rights Baseline: zero Target: 4 Means of Verification: Campaign report | March-December 2019 | Communication Group, UN GTG | TBD |
| Activity 1.5: Collectively contribute to in-country Beijing+25 review (including data collection, verification meetings, presentation of the report, etc.) | Indicator 1.4: Country review developed, verified by key stakeholders, submitted by the State Baseline: no Target: yes by May 2019 Means of Verification: Country Beijing +25 Review Report | May of 2019 | UN Women | TBD |
| OUTCOME 2: The UNCT enhanced performance and accountability on gender equality and women's rights, and include systematic gender mainstreaming in the UNCT processes and national legal frameworks |  |  |  |  |
| OUTPUT 2.1: UNCT has system in place for gender sensitive planning, programming, monitoring, reporting and evaluation |  |  |  |  |
| Planned Activities | Indicators | Timeline | Responsibility | Budget |
| Activity 2.1.1: Jointly with consultant and other UN interagency groups develop and introduce instruments to mainstream gender through UNDAF RG, including planning and monitoring instruments for tracking GEWE results, activities and budget allocations | Indicator 2.1.1.1: UNDAF M&E framework and reporting modality reviewed to better reflect gender UNCT commitments and financial contributions Baseline: no Target: yes Means of Verification: UNDAF Joint Work Plans and reports Indicator 2.1.1.2: Number of Outcome and Output indicators disaggregated by sex and age Baseline: TBD Target: increase by 30% Means of Verification: UNDAF Joint Work Plans Indicator 2.1.1.3: Instructions for gender sensitive reporting developed Baseline: no Target: yes Means of Verification: Instructions for gender sensitive reporting | Annually | Result Group Chairs Relevant UN interagency groups UN GTG | Staff time |
| Activity 2.1.2. Identify priority issues and prepare a CN for Joint Programme focused on addressing the key and cross-cutting gender issues | Indicator 2.1.2: Number of CN for JP developed Baseline: zero Target: one by the end of 2019 Means of Verification: Concept Note | Ocotber 2019 | UN GTG | TBD |
| Activity 2.1.4: Prepare the Annual Report on the implementation of the Gender ScoreCard | Indicator 2.1.4: Annual report on the implementation of the Gender Scorecard developed Baseline: no Target: yes Means of Verification: Annual Report | December 2019 | UN GTG via UN Women | Staff time |
| OUTPUT 3: UNCT demonstrate leadership and the organisational culture conducive to gender equality and have capacities and to coordinate the actions for the advancement of gender equality |  |  |  |  |
| Planned Activities | Indicators | Timeline | Responsibility | Budget |
| Activity 3.1: Present to UNCT and agree on conducting Gender Capacity Assessment for the UNCT | Indicator 3.1: Timeframes for Gender Capacity Assessment approved by UNCT Baseline: no Target: yes Means of Verification: UNCT minutes | March 2019 | RC, UN GTG | TBD |
| Activity 3.2: Organise capacity development event(s) for UNCT/UN GTG on gender equality and women’s rights (for example on SDGs or similar). | Indicator 3.2: Capacity development for UNCT on gender equality Baseline: zero in 2018 Target: at least one in 2018 Means of Verification: Capacity Development Report | 3rd and 4th quarter of 2019 | UN Women, UN GTG | TBD |